## 开发计划
VX42 | Excel Gantt Chart | [6 empty] | © 2006 Vertex42 LLC
灵感分享网站开发计划
| 创建日期: | 2012-03-26
| 启动日期: | 2012-04-01 | 上线日期： | 2012-06-01 |  |  |  |  | 0 | 2012-04-02 | 2012-04-03 | 2012-04-04 | 2012-04-05 | 2012-04-06 | 2012-04-09 | 2012-04-10 | 2012-04-11 | 2012-04-12 | 2012-04-13 | 2012-04-16 | 2012-04-17 | 2012-04-18 | 2012-04-19 | 2012-04-20 | 2012-04-23 | 2012-04-24 | 2012-04-25 | 2012-04-26 | 2012-04-27 | 2012-04-30 | 2012-05-01 | 2012-05-02 | 2012-05-03 | 2012-05-04 | 2012-05-07 | 2012-05-08 | 2012-05-09 | 2012-05-10 | 2012-05-11 | 2012-05-14 | 2012-05-15 | 2012-05-16 | 2012-05-17 | 2012-05-18 | 2012-05-21 | 2012-05-22 | 2012-05-23 | 2012-05-24 | 2012-05-25 | 2012-05-28 | 2012-05-29 | 2012-05-30 | 2012-05-31 | 2012-06-01 | 2012-06-04 | 2012-06-05 | 2012-06-06 | 2012-06-07 | 2012-06-08 | 2012-06-11 | 2012-06-12 | 2012-06-13 | 2012-06-14 | 2012-06-15 | 2012-06-18 | 2012-06-19 | 2012-06-20 | 2012-06-21 | 2012-06-22 | 2012-06-25 | 2012-06-26 | 2012-06-27 | 2012-06-28 | 2012-06-29 | 2012-07-02 | 2012-07-03 | 2012-07-04 | 2012-07-05 | 2012-07-06 | 2012-07-09 | 2012-07-10 | 2012-07-11 | 2012-07-12 | 2012-07-13 | 2012-07-16 | 2012-07-17 | 2012-07-18 | 2012-07-19 | 2012-07-20 | 2012-07-23 | 2012-07-24 | 2012-07-25 | 2012-07-26 | 2012-07-27 | 2012-07-30 | 2012-07-31 | 2012-08-01 | 2012-08-02 | 2012-08-03 | 2012-08-06 | 2012-08-07 | 2012-08-08 | 2012-08-09 | 2012-08-10 | 2012-08-13 | 2012-08-14 | 2012-08-15 | 2012-08-16 | 2012-08-17 | 2012-08-20 | 2012-08-21 | 2012-08-22 | 2012-08-23 | 2012-08-24 | 2012-08-27 | 2012-08-28 | 2012-08-29 | 2012-08-30 | 2012-08-31 | 2012-09-03 | 2012-09-04 | 2012-09-05 | 2012-09-06 | 2012-09-07 | 2012-09-10 | 2012-09-11 | 2012-09-12 | 2012-09-13 | 2012-09-14 | 2012-09-17 | 2012-09-18 | 2012-09-19 | 2012-09-20 | 2012-09-21 | 2012-09-24 | 2012-09-25 | 2012-09-26 | 2012-09-27 | 2012-09-28 | 2012-10-01 | 2012-10-02 | 2012-10-03 | 2012-10-04 | 2012-10-05 | 2012-10-08 | 2012-10-09 | 2012-10-10 | 2012-10-11 | 2012-10-12 | 2012-10-15 | 2012-10-16 | 2012-10-17 | 2012-10-18 | 2012-10-19 | 2012-10-22 | 2012-10-23 | 2012-10-24 | 2012-10-25 | 2012-10-26 | 2012-10-29 | 2012-10-30 | 2012-10-31 | 2012-11-01 | 2012-11-02 | 2012-11-05 | 2012-11-06 | 2012-11-07 | 2012-11-08 | 2012-11-09 | 2012-11-12 | 2012-11-13 | 2012-11-14 | 2012-11-15 | 2012-11-16 | 2012-11-19 | 2012-11-20 | 2012-11-21 | 2012-11-22 | 2012-11-23 | 2012-11-26 | 2012-11-27 | 2012-11-28 | 2012-11-29 | 2012-11-30 | 2012-12-03 | 2012-12-04 | 2012-12-05 | 2012-12-06 | 2012-12-07 | 2012-12-10 | 2012-12-11 | 2012-12-12 | 2012-12-13 | 2012-12-14 | 2012-12-17 | 2012-12-18 | 2012-12-19 | 2012-12-20 | 2012-12-21 | 2012-12-24 | 2012-12-25 | 2012-12-26 | 2012-12-27 | 2012-12-28 | 2012-12-31 | 2013-01-01 | 2013-01-02 | 2013-01-03 | 2013-01-04 | 2013-01-07 | 2013-01-08 | 2013-01-09 | 2013-01-10 | 2013-01-11 | 2013-01-14 | 2013-01-15 | 2013-01-16 | 2013-01-17 | 2013-01-18 | 2013-01-21 | 2013-01-22 | 2013-01-23 | 2013-01-24 | 2013-01-25 | 2013-01-28 | 2013-01-29 | 2013-01-30 | 2013-01-31 | 2013-02-01 | 2013-02-04 | 2013-02-05 | 2013-02-06 | 2013-02-07 | 2013-02-08 | 2013-02-11 | 2013-02-12 | 2013-02-13 | 2013-02-14 | 2013-02-15 | 2013-02-18 | 2013-02-19 | 2013-02-20 | 2013-02-21 | 2013-02-22 | 2013-02-25 | 2013-02-26 | 2013-02-27 | 2013-02-28 | 2013-03-01
序号 | 任务 | 负责人 | 计划开始 | 计划结束 | 实际开始 | 实际结束 | 周期 (天) | 进度 | 2012-04-02: 2012-04-02; 2012-04-09: 2012-04-09; 2012-04-16: 2012-04-16; 2012-04-23: 2012-04-23; 2012-04-30: 2012-04-30; 2012-05-07: 2012-05-07; 2012-05-14: 2012-05-14; 2012-05-21: 2012-05-21; 2012-05-28: 2012-05-28; 2012-06-04: 2012-06-04; 2012-06-11: 2012-06-11; 2012-06-18: 2012-06-18; 2012-06-25: 2012-06-25; 2012-07-02: 2012-07-02; 2012-07-09: 2012-07-09; 2012-07-16: 2012-07-16; 2012-07-23: 2012-07-23; 2012-07-30: 2012-07-30; 2012-08-06: 2012-08-06; 2012-08-13: 2012-08-13; 2012-08-20: 2012-08-20; 2012-08-27: 2012-08-27; 2012-09-03: 2012-09-03; 2012-09-10: 2012-09-10; 2012-09-17: 2012-09-17; 2012-09-24: 2012-09-24; 2012-10-01: 2012-10-01; 2012-10-08: 2012-10-08; 2012-10-15: 2012-10-15; 2012-10-22: 2012-10-22; 2012-10-29: 2012-10-29; 2012-11-05: 2012-11-05; 2012-11-12: 2012-11-12; 2012-11-19: 2012-11-19; 2012-11-26: 2012-11-26; 2012-12-03: 2012-12-03; 2012-12-10: 2012-12-10; 2012-12-17: 2012-12-17; 2012-12-24: 2012-12-24; 2012-12-31: 2012-12-31; 2013-01-07: 2013-01-07; 2013-01-14: 2013-01-14; 2013-01-21: 2013-01-21; 2013-01-28: 2013-01-28; 2013-02-04: 2013-02-04; 2013-02-11: 2013-02-11; 2013-02-18: 2013-02-18; 2013-02-25: 2013-02-25
一 | 第一次迭代 | Dream Ranger Team | 2012-04-02 | 2012-05-02 |  |  | 26
1 | 设计 | Dream Ranger Team | 2012-04-02 | 2012-04-15
1.1 | 需求分析 | Adler | 2012-04-02 | 2012-04-03 | 2012-03-26 | 2012-03-30 |  | 100%
1.2 | 概要设计 | Adler | 2012-04-04 | 2012-04-06
1.3 | 网站整体风格设计 | L.Robin | 2012-04-02 | 2012-04-06
1.4 | 原型设计 | Adler、Lawliet | 2012-04-07 | 2012-04-13
1.5 | DB设计 | Adler、Lawliet | 2012-04-14 | 2012-04-14
1.6 | 详细设计 | Adler、Lawliet | 2012-04-15 | 2012-04-15
2 | 开发 | Dream Ranger Team | 2012-04-16 | 2012-04-26
3 | 测试 | Dream Ranger Team | 2012-04-27 | 2012-05-02
二 | 第二次迭代 | Dream Ranger Team | 2012-05-03 | 2012-05-17 |  |  | 15
1 | 设计 | Dream Ranger Team
1.1 | 需求分析 | Adler、Lawliet
1.2 | 概要设计 | Adler、Lawliet
1.4 | 原型设计 | Adler、Lawliet
1.6 | 详细设计 | Adler、Lawliet
2 | 开发 | Dream Ranger Team
3 | 测试 | Dream Ranger Team
三 | 第三次迭代 | Dream Ranger Team | 2012-05-18 | 2012-05-26 |  |  | 9
1 | 设计 | Dream Ranger Team
1.1 | 需求分析 | Adler、Lawliet
1.2 | 概要设计 | Adler、Lawliet
1.4 | 原型设计 | Adler、Lawliet
1.6 | 详细设计 | Adler、Lawliet
2 | 开发 | Dream Ranger Team
3 | 测试 | Dream Ranger Team
四 | 上线部署 | Dream Ranger Team | 2012-05-27 | 2012-06-01 |  |  | 6
1 |  | Dream Ranger Team
Note on I1: Limited Use Policy The spreadsheet is for your personal use only. You may customize it to suit your needs, but it may not be sold, distributed, or placed on a public server (i.e. the internet), without the written consent of Vertex42 LLC. No Warranties THE SOFTWARE AND ANY RELATED DOCUMENTATION ARE PROVIDED TO YOU "AS IS." VERTEX42, LLC MAKES NO WARRANTIES, EXPRESS OR IMPLIED, AND EXPRESSLY DISCLAIMS ALL REPRESENTATIONS, ORAL OR WRITTEN, TERMS, CONDITIONS, AND WARRANTIES, INCLUDING BUT NOT LIMITED TO, IMPLIED WARRANTIES OF MERCHANTABILITY, FITNESS FOR A PARTICULAR PURPOSE, AND NONINFRINGEMENT. WITHOUT LIMITING THE ABOVE YOU ACCEPT THAT THE SOFTWARE MAY NOT MEET YOUR REQUIREMENTS, OPERATE ERROR FREE, OR IDENTIFY ANY OR ALL ERRORS OR PROBLEMS, OR DO SO ACCURATELY. This Agreement does not affect any statutory rights you may have as a consumer. Some states do not allow the limitation or exclusion of liability for incidental or consequential damages, so the above limitation may not apply to you. Limitation of Liability IN NO EVENT SHALL VERTEX42, LLC BE LIABLE TO YOU, FOR ANY DAMAGES, INCLUDING ANY LOST PROFITS, LOST SAVINGS, OR ANY OTHER DIRECT, INDIRECT, SPECIAL, INCIDENTAL, OR CONSEQUENTIAL DAMAGES ARISING FROM THE USE OR THE INABILITY TO USE THE SOFTWARE (EVEN IF WE OR AN AUTHORIZED DEALER OR DISTRIBUTOR HAS BEEN ADVISED OF THE POSSIBILITY OF THESE DAMAGES), OR ANY MISTAKES AND NEGLIGENCE IN DEVELOPING THIS SOFTWARE, OR FOR ANY CLAIM BY ANY OTHER PARTY. THE ORGANIZATION, BUSINESS, OR PERSON USING THIS SOFTWARE BEARS ALL RISKS AND RESPONSIBILITY FOR THE QUALITY AND PERFORMANCE OF THIS SOFTWARE. Somes states do not allow the limitation or exclusion of liability for incidental or consequential damages, so the above limitation may not apply to you.